Each day: Morning (2–3 hrs) learning/skill building · Midday (2–3 hrs) building infrastructure or client work · Afternoon (1–2 hrs) outreach/sales. In Month 3, client work moves to morning.

## Month 1 — Days 1–30

Theme: Learn, Build, Launch Outreach

### Week 1 — Days 1–6

Goal: Set up the agency skeleton + start learning Google Ads  ·  6–7 hrs/day

Day 1 — Agency Foundation (6 hrs)

Morning · 3 hrs

- Choose agency name and check domain availability

- Buy domain + set up Google Workspace (professional email: you@agencyname.com)

- Create accounts: Google Ads Manager, Meta Business Suite, Canva, Notion

Midday · 2 hrs

- Set up Notion workspace — your operating system

  - Create pages: Prospects, Active Clients, Learning Log, SOPs, Templates

- Open GoHighLevel free trial (gohighlevel.com) — core tool for client CRM, email automation, and reputation management. $97/mo after trial but replaces 5 other tools.

Afternoon · 1 hr

- Watch "How to start a local marketing agency in 2025" on YouTube (2–3 perspectives)

- Write your agency's one-sentence positioning: who you serve + what you get them

Day 2 — Google Ads: Core Concepts (7 hrs)

Morning · 3 hrs

- Google Skillshop (google.com/skillshop) — complete "Google Ads Search — Foundations" module (~2.5 hrs, free)

- Take notes in Notion

Midday · 2 hrs

- Watch Ben Heath on YouTube: "Google Ads for Local Businesses" (1 hr)

- Set up a Google Ads Manager account (MCC account — manage multiple client accounts from one login)

- Watch: "How to structure a Google Ads account for a local service business"

Afternoon · 2 hrs

- Google Skillshop: "Search Campaigns" module

- Read: Google Local Services Ads setup guide (Google's own documentation)

Day 3 — Google Ads: Search Campaigns + LSAs (7 hrs)

Morning · 3 hrs

- Finish Google Skillshop "Search Campaigns" module

- Practice: Build a fake Google Search campaign for a made-up HVAC company — 3 ad groups, 10 keywords each, 3 ads per ad group. No money spent. Just build it.

Midday · 2 hrs

- Apply for Google Local Services Ads verification as an agency (takes time to process — get it in early)

- Watch: "Google Local Services Ads complete setup" on YouTube

- Learn: How LSA bidding works vs. Search (pay per lead vs. pay per click)

Afternoon · 2 hrs

- Google Skillshop: "Measurement" module — conversion tracking is essential

- Learn: How to set up Google Tag Manager + conversion tracking on a website

- Practice: Install GTM on a test site (WordPress or Squarespace free trial)

Day 4 — Meta Ads: Core Concepts (6 hrs)

Morning · 3 hrs

- Meta Blueprint (business.facebook.com/business/learn) — complete "Introduction to Meta Advertising" + "Facebook Ads Manager" modules (~2 hrs)

- Watch Ben Heath on YouTube: "Meta Ads for local businesses" (45 min)

Midday · 2 hrs

- Set up a Meta Business Suite account

- Learn: Campaign objectives — Leads vs. Traffic vs. Conversions (for local businesses, Leads is usually right)

- Practice: Build a fake Meta Leads campaign for a med spa — audiences, ad set structure, budget

Afternoon · 1 hr

- Learn: Meta Pixel setup + lead form ads (huge for local businesses — no landing page needed)

- Bookmark: Meta's Ads Manager Help Center for reference

Day 5 — Local SEO + Google Business Profile (7 hrs)

Morning · 3 hrs

- Read: Whitespark's "Local SEO Guide" (whitespark.ca/local-search-ranking-factors) — annual survey of what actually moves local rankings

- Watch: "Google Business Profile complete setup 2025" on YouTube (1 hr)

- Learn: What NAP consistency means and why it matters

Midday · 2 hrs

- Create a free BrightLocal account (brightlocal.com) — run citation audits for prospects. Free trial gives a few reports.

- Practice: Run a citation audit on a local business using their tool

- Learn: Local competitor analysis — search their keyword + city, note who's in the top 3 map pack and why

Afternoon · 2 hrs

- Read: Moz Local SEO Learning Center (moz.com/learn/seo/local) — especially the local ranking factors section

- Learn: Schema markup for local businesses (LocalBusiness schema) — Merkle's Schema Markup Generator handles this without coding

- Learn: Review generation best practices and what violates Google's guidelines

Day 6 — GoHighLevel + CRM/Email Automation (6 hrs)

Morning · 3 hrs

- YouTube: "GoHighLevel for beginners complete walkthrough"

- Learn: How to set up a pipeline (stages: Lead → Contacted → Discovery Booked → Proposal Sent → Closed)

- Set up your own agency pipeline in GoHighLevel to track your own prospects

Midday · 2 hrs

- Learn: How to build an automation (lead comes in → sends email → sends SMS → task created for follow-up)

- Practice: Build a simple lead nurture sequence (3 emails) for a fake HVAC company

- Learn: How to set up reputation management in GHL (automated review request texts)

Afternoon · 1 hr

- Week 1 review: What do you know well? What needs more time?

- Update Notion Learning Log and list gaps to fill next week

### Week 2 — Days 7–12

Goal: Finish learning core skills + build all agency materials  ·  6–7 hrs/day

Day 7 — Agency Website (6 hrs)

Morning · 2 hrs

- Map out 5-page website: Home, Services, About, Case Studies (placeholder), Contact

- Write homepage in a Google Doc first — who you serve, what you do, why them, CTA (free audit)

Midday · 3 hrs

- Build website on Squarespace or Webflow (Squarespace is faster, Webflow is more flexible)

- Clean, minimal design — reference other local marketing agencies but don't copy

- Complete Home page and Services page today

Afternoon · 1 hr

- Write Services page copy: paid ads, local SEO, email/CRM, website

- Add "Free Local Marketing Audit" CTA button on every page — this is your offer

Day 8 — Agency Materials: Proposal + Contract (7 hrs)

Morning · 3 hrs

- Build proposal template in Google Docs or Canva

- Sections: Executive Summary · What We Found · Recommended Plan (3 tiers) · Timeline · Numbers · Investment · Next Steps

- Design it cleanly — this is a sales tool

Midday · 2 hrs

- Build 3-tier pricing one-pager:

  - Foundation: $2,000/mo

  - Growth: $3,500/mo (recommended)

  - Full-Service: $5,000/mo

- Write what's included in each tier

Afternoon · 2 hrs

- Get a simple service agreement — use Bonsai (hellobonsai.com) or AND.CO (~$25/mo, handles contracts + invoicing)

- Customize: 50% upfront, monthly on 1st, 3-month minimum, ad spend billed separately

- Add: what you will and won't do, ownership of accounts

Day 9 — Keyword Research + Competitive Analysis Practice (7 hrs)

Morning · 3 hrs

- Learn keyword research for local service businesses:

  - Google Keyword Planner (free in Google Ads)

  - Semrush free (10 queries/day) or Ahrefs Webmaster Tools (free for your own domain)

- Practice: Research "HVAC Pittsfield MA", "plumber Gloucester MA" — find search volumes, competition, cost per click

Midday · 2 hrs

- Practice: Full competitive analysis for a local HVAC company (pretend they're a prospect)

  - Who's in the top 3 map pack? Why?

  - Who's running Google ads? What do their ads say?

  - Review count gap? Website quality comparison?

- Write it up as a fake audit in Notion — practice presenting it like you would to a client

Afternoon · 2 hrs

- Learn: Google Search Console and what data it shows

- Learn: Google PageSpeed Insights — how to read scores and what recommendations matter for local businesses

- Learn: How to check if a site has schema markup (View Source → search for "application/ld+json")

Day 10 — Ad Creative + Canva (6 hrs)

Morning · 2 hrs

- Learn: What makes a good local service ad

- Study 10 real painting/HVAC/plumbing Facebook ads via Meta Ad Library (facebook.com/ads/library)

- Notice: What angles do they use? Before/after, reviews, pricing, urgency?

Midday · 2 hrs

- Build 5 ad creative templates in Canva:

  - Before/After · Review highlight · "Call now" · Seasonal offer · Team/credibility

- Save as Canva Brand Kits

Afternoon · 2 hrs

- Learn: Google Responsive Search Ads — 15 headlines and 4 descriptions

- Write a full RSA for a fake exterior painting company: 15 headlines, 4 descriptions, 2 sitelinks, 1 callout

- Practice writing Meta ad copy: hook line, body, CTA for the same painting company

Day 11 — GoHighLevel Deep Dive + Reporting Setup (7 hrs)

Morning · 3 hrs

- GoHighLevel: Learn how to white-label it for clients (resell GHL as your own client portal)

- Set up a template client account with:

  - Pipeline stages · Lead capture form · 3-email follow-up sequence · Review request automation

- This becomes your "done-for-you CRM" you offer clients

Midday · 2 hrs

- Build client reporting template in Google Slides or Loom:

  - Monthly report: Ad spend, leads generated, cost per lead, Google reviews count, GBP views, website traffic

  - One page / 5 minutes — clients don't read long reports

- Learn Loom (loom.com) for screen walkthrough reports

Afternoon · 2 hrs

- Set up Google Analytics 4 on your agency website

- Practice: Connect a Google Ads account to GA4

- Learn: How to set up a conversion in GA4 (form submission = conversion)

Day 12 — Prospect List Building (6 hrs)

Morning · 2 hrs

- Define ICP (ideal client profile):

  - Home services: HVAC, plumbing, roofing, electrical, painting — 2–15 employees, operating 3+ years, has a website but under 30 Google reviews

  - Geography: Berkshire County (Pittsfield, Lenox, Stockbridge, Great Barrington, Lee, Dalton, North Adams, Williamstown) + North Shore (Salem, Gloucester, Beverly, Newburyport, Ipswich, Marblehead)

Midday · 3 hrs

- Build prospect list — target 60 total businesses via Google Maps (search each service + town)

- For each: review count, running Google Ads (Y/N), website quality score (1–10)

- Enter into Google Sheet: Business name, owner name, email, phone, city, service type, review count, ads running, quality score, notes

- Score each prospect 1–5. A 5 = obvious gap + high-ticket service + no ads running.

Afternoon · 1 hr

- Find owner names + emails:

  - LinkedIn: search [business name] or [owner name] + [city] + [trade]

  - Website: check /about, /contact, or footer

  - Hunter.io free tier: 25 lookups/mo · Apollo.io free tier: 50 credits/mo

### Week 3 — Days 13–18

Goal: Launch outreach + finish website  ·  6–7 hrs/day

Day 13 — Email Setup + First Outreach Wave (7 hrs)

Morning · 2 hrs

- Set up cold email infrastructure:

  - Buy a secondary domain (never cold email from your main domain)

  - Set up Google Workspace on the secondary domain

  - Configure SPF, DKIM, DMARC records (follow Google's guide — stops emails going to spam)

  - Warm up inbox: Instantly.ai or Lemlist free trial (send to warmup network for 2 weeks before real cold email)

Midday · 3 hrs

- Write your 5-email cold sequence, personalized for home services

- Personalize the first 20 emails manually — research each business: competitors, review count, running ads, one specific line about their situation

Afternoon · 2 hrs

- Send first 10 cold emails manually from Gmail (while secondary domain warms up)

- Set up follow-up reminders in Notion: Day 4, 8, 13, 19 for each prospect

- Log all 10 in GHL pipeline under "Contacted"

Days 14–15 — Direct Mail Campaign

Day 14 Morning · 3 hrs

- Write direct mail letter — one page, on agency letterhead:

  - "I searched [service] in [their town] and noticed..." → specific gap → free audit offer

  - Include a QR code linking to your "Free Audit" landing page

  - Handwrite or print a P.S. at the bottom — it always gets read

Day 14 Midday · 2 hrs

- Design letterhead in Canva

- Print first 20 letters (home printer or FedEx Office)

- Hand-address the envelopes — significantly increases open rates vs. printed labels

Day 14 Afternoon · 1 hr

- Send the letters — first class mail

- Log in Notion: date sent, expected delivery window

Day 15

- Morning (3 hrs): Build second GHL client template for med spa — different pipeline stages, email sequence, review request timing

- Midday (2 hrs): Write a full set of Google Ads keywords for a dental office (broad, phrase, exact match types)

- Afternoon (1 hr): Send outreach emails 11–20. Follow up on Day 4 emails from Day 13.

Days 16–18 — Outreach Rhythm + Website Finish

Day 16 · 6 hrs

- Morning: Finish agency website — About page, Case Studies placeholder ("Client results coming soon — in pilot phase"), Contact page with audit form

- Midday: Set up "Free Local Marketing Audit" landing page — headline, 3 bullet points of what they get, form (name, business, phone, email, city, business type)

- Afternoon: Send outreach batch 21–30. Follow-up wave 2.

Day 17 · 7 hrs

- Morning: Watch 3 case study videos of local marketing agencies (YouTube). What metrics did they track? How did they present results? What did clients care about most?

- Midday: Build discovery call script in Notion. Practice out loud — record on Loom and watch it back.

- Afternoon: Send outreach batch 31–40. Follow-up wave 3.

Day 18 · 6 hrs

- Morning: LinkedIn outreach — connect with 10 local business owners. Message: "Hey [Name], I work with [service type] businesses in [region] on their local marketing. Not pitching — just good to be connected." No ask yet.

- Midday: Review prospect list — who opened emails? Prioritize those for phone follow-up.

- Afternoon: Call 5 prospects who haven't replied. "Hey, I sent you a quick email about your Google presence — just wanted to see if it made sense to chat for 15 minutes." Expect voicemails. That's fine.

### Week 4 — Days 19–30

Goal: First discovery calls booked + agency fully operational

Days 19–24 — Daily Pattern (6–7 hrs)

Morning · 2 hrs

Learning — go deeper on one skill. Week 4 focus: conversion tracking, Google Analytics 4, and how to prove ROI to clients.

Midday · 2–3 hrs

Outreach — new prospects (10/day), follow-ups on existing sequences, LinkedIn connections.

Afternoon · 1–2 hrs

Discovery calls when booked, prep for calls, send follow-up emails after calls.

#### Specific daily learning

- Day 19: Conversion tracking in Google Ads (call tracking, form tracking)

- Day 20: How to read a Google Ads dashboard — what to optimize, what to ignore

- Day 21: Local SEO audit from scratch (BrightLocal trial, Semrush free, manual Google checks)

- Day 22: How to write a local content page (location + service keyword targeting)

- Day 23: How to set up a Mailchimp or GHL email campaign from scratch

- Day 24: Website CRO audit — heatmaps (Hotjar free), page speed, mobile experience

Days 25–30 — First Discovery Calls

- When a call is booked: spend 30 min researching that business first. Pull Google reviews, run a quick competitor analysis, screenshot their site on mobile.

- After each call: send a follow-up email same day

- Proposals: write within 48 hours of discovery call, using their exact words

- Schedule walkthrough call 3–5 days after sending proposal

#### Day 30 targets

- 60 prospects contacted (email + some phone + some LinkedIn)

- 3–5 discovery calls completed or booked

- 1–2 proposals sent

- Agency website live

- All materials built (proposal template, contract, pricing, reporting template)

## Month 2 — Days 31–60

Theme: Close First Clients + Start Delivery

### Weeks 5–6 — Days 31–42

Goal: Close first 1–2 clients. Heavy sales mode.  ·  6–7 hrs/day

Daily Structure

Morning · 2 hrs — Skill deepening

Week 5: Google Ads optimization (quality scores, negative keywords, bid adjustments, ad scheduling)

Week 6: Meta Ads advanced (lookalike audiences, retargeting, creative testing)

Midday · 2–3 hrs — Sales activity

Send 10 new outreach emails. Follow-up sequences for all active prospects. Run discovery calls, log notes, write proposals. Proposal walkthroughs.

Afternoon · 1–2 hrs — Proposals + follow-up

Write personalized proposal within 48 hours of each discovery call. Follow up on sent proposals (day 3, day 7, checking-in call). Handle objections.

Key Tasks — Days 31–42

- Day 31: Review all open prospects. Who needs a follow-up? Who went cold? Segment your list.

- Day 33: If no discovery calls yet — call 10 prospects directly. "I have 15 minutes free Thursday. Worth a quick call?"

- Day 35: Set up call recording (Otter.ai) — reviewing your own calls is the fastest way to improve.

- Day 37: Re-evaluate offer. If nobody's biting, consider a one-month pilot at $1,500 to get in the door.

- Day 40: Do a full mock run of your discovery call script out loud. Time yourself.

- Day 42: You should have at minimum 1 client signed or 1 proposal actively being considered.

### Weeks 7–8 — Days 43–60

Goal: Sign clients 1–2. Begin delivery prep.  ·  7 hrs/day

Days 43–50 — Close + Onboard

Morning · 2 hrs — Onboarding prep

- Build client onboarding checklist in Notion:

  - Signed contract · First payment received · Accounts access granted (Google Ads, Meta, GA, GBP, website) · Onboarding questionnaire sent + completed · Kickoff call scheduled

- Build onboarding questionnaire (Google Form or Typeform):

  - Business info (NAP, hours, service areas)

  - Target customer demographics, competitors, past marketing history, current lead sources

  - What success looks like to them in 90 days

Midday · 3 hrs — Campaign builds

- Days 43–45: Set up client Google Ads account + link to your Manager account

- Days 46–48: Build first campaign — HVAC or home service Google Search campaign

- Days 49–50: Set up conversion tracking (CallRail $40/mo or Google Ads call tracking, form submissions)

Afternoon · 2 hrs — Outreach continues

Do not stop outreach because you have 1–2 clients. Keep sending 8–10 emails/day. You want 3–4 clients in Month 3, not 1–2.

Days 51–60 — Full Delivery Prep

Morning · 3 hrs

Client work — campaign builds, GBP optimization, review system setup, CRM setup.

Midday · 2 hrs

Outreach — emails, follow-ups, calls.

Afternoon · 2 hrs

Learning — fill in gaps as they come up during client work.

#### Specific daily tasks

- Day 51: GBP optimization for first client — fill every field, add photos, enable messaging, create first post

- Day 52: Set up review request automation in GHL — text goes out 24 hours after job completion

- Day 53: Set up client CRM in GHL — import existing contacts, configure pipeline stages

- Day 54: Build client lead nurture email sequence (3–6 emails)

- Day 55: Google Ads goes live — monitor closely for first 3 days

- Day 56: Set up LSA account for client and submit for verification (takes 1–2 weeks)

- Day 57: Review search terms report. Add negative keywords. Note which keywords triggered impressions.

- Day 58: Write first client report — Week 1 snapshot. Send via Loom. Keep it under 5 minutes.

- Day 59: Discovery call prep — you should have more prospects in the pipeline. Prep for Week 9 calls.

- Day 60: Mid-point review — how many clients? What's working in outreach? What's not?

#### Day 60 targets

- 1–2 paying clients (ideally 2)

- Campaigns live and generating first leads/data

- $2,000–$7,000 MRR

- 100+ prospects contacted total

- 2–3 more in proposal or discovery stage

## Month 3 — Days 61–90

Theme: Deliver Results + Scale to 3–4 Clients

### Weeks 9–10 — Days 61–75

Goal: Optimize campaigns, get early results, sign clients 3–4  ·  7 hrs/day

Daily Structure (flipped from Month 1)

Morning · 3 hrs

Client work — this is now the priority.

Midday · 2 hrs

New outreach + follow-ups.

Afternoon · 2 hrs

Sales calls, proposals, learning.

Client Work — Days 61–75

Days 61–63: Campaign optimization round 1

- Review first 2 weeks of Google Ads data

- What search terms are converting? → Raise bids on those

- What's wasting money? → Add as negative keywords

- Ad CTR under 3%? → Rewrite low-performing ads

Days 64–66: Local SEO — first wins

- GBP: Post 2x/week (service spotlight, before/after, seasonal offer)

- Citations: Submit to top 10 directories — Yelp, Angi, Houzz, BBB, HomeAdvisor, Nextdoor, Apple Maps, Bing Places, Yellow Pages, Facebook

- NAP check: name, address, phone identical everywhere

- Reviews: Is the automation sending? If not, text clients manually.

Days 67–69: CRM + email sequence audit

- Are leads being captured in GoHighLevel?

- Is the follow-up sequence triggering correctly?

- Call 2–3 leads that came in but didn't convert — listen to why

Days 70–72: Landing page optimization

- Review landing page conversion rate (form submissions ÷ visitors)

- Under 5%? Common issues: slow load, no clear headline, no trust signals, poor mobile design

- Quick fixes: add Google review count, add phone number at top, add a before/after photo above the fold

Days 73–75: Month 1 client reports

- Pull all data: leads generated, cost per lead, Google review count change, GBP views, website traffic

- Record a 5-minute Loom video walking through the dashboard

- Frame around their onboarding goals: "You said you wanted more leads in the slow season — here's what we're seeing so far"

- Schedule 30-minute review call

Outreach + Sales — Days 61–75

- Continue 8–10 cold emails/day to new prospects

- By now your secondary domain is warmed up — use it for higher volume

- Expand to a second vertical: med spa or dental

- Med spa hook: "Searched 'botox [city]' — [Competitor] is running ads. You're on page 2. For a service people book when they're ready to spend, that's expensive real estate to give up."

- You should be closing 1 new client every 2–3 weeks at this point

### Weeks 11–13 — Days 76–90

Goal: 3–4 clients, repeatable delivery system, first case study  ·  6–7 hrs/day

Days 76–82 — Build Delivery SOPs

Now that you've done this once or twice, document everything:

- Day 76: "New Client Onboarding SOP" — step by step, what happens in Week 1 of every new client

- Day 77: "Google Ads Launch SOP" — campaign structure, naming convention, conversion tracking, go-live checklist

- Day 78: "Local SEO Month 1 SOP" — GBP optimization steps, citation submission list, review system setup

- Day 79: "Monthly Reporting SOP" — what data to pull, how to frame it, what to include

- Day 80: "Discovery Call SOP" — the questions, the flow, what to listen for

- Day 81: Review all SOPs. These are your hiring documents later — the first thing a VA or contractor would read.

- Day 82: Build a client "Welcome Kit" — short PDF or Notion page: what to expect in month 1, communication norms, how to give account access, what you need from them

Days 83–87 — Case Study Prep + Referral Activation

Day 83

Pull your best early results data. Even 30 days makes a case study: "In the first 30 days, [Client] went from 12 to 24 Google reviews and generated 8 qualified leads from Google Ads at $38 per lead." Write it up.

Day 84

Ask your first client for a testimonial: "Hey [Name], I'm building out a case study from our first month together. Could you shoot me a quick 2–3 sentence note about the experience so far? Doesn't need to be polished."

Day 85

Add case study section to your website. Even one case study transforms your credibility.

Day 86

Referral activation: "Do you know any other [trade] businesses in the area who could use help with their marketing? I work on referrals and would give you a month free if someone you refer signs on."

Day 87

LinkedIn — post about your agency. One post about what you're learning or a result you got (no client names unless permitted). This plants a flag and starts inbound.

Days 88–90 — Review + Month 4 Planning

Day 88: Full business review

- How many clients? What's your MRR?

- What's working in outreach?

- Average close rate (calls → clients)?

- What's taking the most time in delivery?

Day 89: Identify your bottleneck

- No clients: problem is outreach or offer — go back to cold email and adjust the angle

- Clients but can't deliver: problem is systems — use SOPs and consider a VA for admin tasks

- Delivery eating all your time: build a contractor roster — a Google Ads freelancer on Upwork you can hand off campaigns to

Day 90: Set Month 4 targets

- 4–5 clients, $8,000–$15,000 MRR

- 1 documented case study

- Referral from at least one existing client

- Outreach fully systematized (not taking more than 1.5 hrs/day)

## Summary Milestones

| Milestone | Target |
| --- | --- |
| Agency name, domain, email, tools set up | Day 1 |
| Core skills learned (Google Ads, Meta, SEO, GHL) | Day 12 |
| All agency materials built | Day 16 |
| First outreach sent | Day 13 |
| First discovery call | Days 21–25 |
| First proposal sent | Days 25–28 |
| First client signed | Days 35–45 |
| First campaigns live | Days 50–55 |
| Second client signed | Days 50–60 |
| First early results data | Days 60–65 |
| Third client signed | Days 65–75 |
| First case study written | Day 85 |
| MRR at Day 90 | $6,000–$15,000 |

The one rule for all 90 days

Never let outreach stop because you're busy with client work.

The biggest mistake new agency owners make is going heads-down on a client, stopping outreach, and then losing that client 3 months later with nothing in the pipeline. Even at 3 clients and full capacity, send 5 emails/day. It takes 20 minutes. The pipeline you build in Month 2 becomes clients in Month 4.