DELKO

90-Day Operating Manual

For Keveen Delgado and Jack Koutrobis

Start date: May 11, 2026

Core Operating Rule Every day must create proof, conversations, or a better system. Do not hide in planning. The agency becomes real when owners start responding, booking calls, and saying yes.

# How to Use This Manual

This document turns the Delko 90-day operating spreadsheet into a readable execution manual. Use the spreadsheet for live tracking and use this manual for strategy, weekly planning, daily rhythm, roles, checklists, and partner accountability.

Start each week with the Weekly Execution Plan and confirm the must-ship asset.

Run each day from the Phase-by-Phase Daily Rhythm, not from random tasks.

Update the CRM and scorecard weekly so outreach and proof stay visible.

Use the Website and Dad Case Study checklist as the first proof engine.

At Day 30, Day 60, and Day 90, make decisions based on scorecard data, not feelings.

## Document Map

| Section | Purpose |
| --- | --- |
| 1. Operating Snapshot | Targets, KPIs, non-negotiables, and the 90-day decision frame. |
| 2. Phase Roadmap | What matters most across Foundation, Outreach, Close + Deliver, and Systemize + Scale. |
| 3. Weekly Execution Plan | Week-by-week priorities, owner lanes, must-ship assets, and decision gates. |
| 4. Daily Operating Rhythm | The actual time-blocked schedule by phase. |
| 5. Website + Dad Case Study Checklist | The first proof-building project and launch checklist. |
| 6. CRM + Scorecard System | How Delko tracks prospects, outreach, calls, proposals, clients, and bottlenecks. |
| 7. Reference Rules | Operating principles, partner lanes, starting offers, and source inputs. |

# 1. Operating Snapshot

The first 90 days should be judged by visible proof, qualified conversations, speed of delivery, and whether Delko can repeat the same system across multiple local businesses.

## 90-Day Targets

| Target | Definition |
| --- | --- |
| Start Date | May 11, 2026 |
| Current Day | 1 |
| Target by Day 14 | Website live + dad case study foundation + 50 qualified prospects |
| Target by Day 30 | Website live, 100+ contacted, 3-5 discovery calls, 1 proposal |
| Target by Day 60 | 1-2 paying clients, dad case study active, $1.5K-$4.5K MRR |
| Target by Day 90 | 3-5 clients, first case study published, repeatable sales/delivery system |
| 80/20 Rule | Every day must create proof, conversations, or a better system |

## KPI Dashboard

| KPI | How It Is Measured | Current | Goal | Status |
| --- | --- | --- | --- | --- |
| Overall Task Progress | Done tasks / total tasks | 0 | 80%+ | Needs Work |
| Website Launch Tasks Done | Website launch checklist | 0 | 100% by Day 7 | Open |
| Dad Case Study Tasks Done | Case study checklist | 0 | 100% by Day 14 | Open |
| Prospects Added | CRM rows with business name | 0 | 50 by Day 14 | Build List |
| Outreach Sent | CRM rows marked Contacted or later | 0 | 100 by Day 30 | Keep Going |
| Discovery Calls Booked | CRM status | 0 | 3-5 by Day 30 | Need Calls |
| Clients Closed | CRM closed won | 0 | 3-5 by Day 90 | Pipeline |

## Daily Non-Negotiables

| Non-Negotiable | Owner | Minimum | Why It Matters |
| --- | --- | --- | --- |
| Update dad case study or client proof | Keveen | 60 minutes | Proof beats promises |
| Add or clean prospects | Jack / Keveen | 5 businesses | Pipeline starts with qualified lists |
| Send or follow up | Jack | 10 touches | Conversations create clients |
| Build one system asset | Keveen | 1 template/SOP/checklist | Systems compound |
| Review CRM | Both | 10 minutes | No leads fall through cracks |
| Cap learning | Keveen | 90 minutes | Avoid hiding in research |

# 2. Phase Roadmap

The spreadsheet has four working phases. This manual keeps the phases simple so Delko can avoid spreading attention across too many services too early.

| Days | Phase | Main Job | Proof of Progress |
| --- | --- | --- | --- |
| Days 1-14 | Foundation | Launch the website, build the dad case study baseline, create the first assets, and reach 50 qualified prospects. | Website live, dad proof captured, CRM live, first audit scripts usable. |
| Days 15-30 | Outreach + Calls | Turn audits into real conversations and proposals while continuing to improve proof. | 100 total touches, 3-5 calls, 1 proposal, one serious buyer. |
| Days 31-60 | Close + Deliver | Close first 1-2 clients or pilots and deliver fast, visible wins. | 1-2 clients, $1.5K-$4.5K MRR, monthly report template, active case study. |
| Days 61-90 | Systemize + Scale | Document delivery, publish proof, keep pipeline alive, and decide the next niche/offer/pricing move. | 3-5 clients target, first case study published, repeatable delivery system. |

# 3. Weekly Execution Plan

## Weekly Strategy Table

| Week | Days | Theme | 80/20 Priority | Must Ship | Success Metric | Decision Gate |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1-7 | Foundation + website launch | Publish credible website and start dad case study | Website live, audit template, CRM live | 25 prospects, 5 outreach, dad baseline captured | Is the offer simple enough to explain? |
| 2 | 8-14 | Case study + outreach sprint | Create proof and start real conversations | Dad foundation live, 50 qualified prospects | 50 prospects, 10 audits, 2 calls booked | Are owners responding to the audit angle? |
| 3 | 15-21 | Audit-led selling | Turn audits into calls | 3-5 personalized audits | 100 total touches, 3 calls booked | Which vertical has strongest pull? |
| 4 | 22-30 | First proposals | Use owner language to sell foundation package | 1-2 proposals | 1 proposal sent, 1 serious buyer | Do we need a lower-friction pilot? |
| 5 | 31-37 | Close first client | Move from conversations to paid pilot | Pilot offer + onboarding checklist | 1 signed pilot or proposal in review | What objection repeats most? |
| 6 | 38-45 | Client delivery begins | Deliver first result fast | Client week 1 report | 1 client live, 100+ total prospects | Is delivery taking too long? |
| 7 | 46-52 | Proof building | Capture before/after and early wins | Before/after proof folder | 2 active opportunities | What tasks can be templated? |
| 8 | 53-60 | Second client push | Repeat what worked | Monthly report template | 1-2 clients, $1.5K-$4.5K MRR | Which package sells easiest? |
| 9 | 61-67 | Optimize delivery | Make client work repeatable | Delivery SOP v1 | 2-3 clients/proposals | Are we ready to raise price? |
| 10 | 68-75 | Scale outreach | Keep pipeline alive while delivering | Referral ask system | 3 active sales conversations | Do we need contractor support? |
| 11 | 76-82 | Systemize | Turn recurring work into SOPs | 5 core SOPs | Delivery time reduced | What should we stop offering? |
| 12 | 83-87 | Case study publish | Turn proof into sales asset | Case study live | 1 case study + testimonial request | Can proof support higher pricing? |
| 13 | 88-90 | Review + next quarter | Decide niche, offer, roles, pricing | Month 4 plan | 3-5 clients target or clear bottleneck | Scale, niche, or reset? |

## Partner Lanes by Week

| Week | Keveen Focus | Jack Focus |
| --- | --- | --- |
| 1 | Website, offer, audit template, dad baseline | Prospect list and first warm messages |
| 2 | Dad GBP/review/lead system, 5 audits | 20-30 outreach touches, follow-ups |
| 3 | Audit improvements, proposal template, call support | Outreach/follow-up/call booking |
| 4 | Proposal + dad progress snapshot | Book calls, handle follow-ups |
| 5 | Refine offer, prepare onboarding | Close, follow up, referrals |
| 6 | GBP, website, reviews, tracking | Keep pipeline warm |
| 7 | Client/dad reporting, SOPs | More outreach and referrals |
| 8 | Fulfillment + report system | Calls/proposals |
| 9 | SOPs, dashboards, case study draft | Outreach 5-10/day |
| 10 | Quality control and reports | Cold/warm/referral campaigns |
| 11 | SOP library, client welcome kit | Referral and nurture |
| 12 | Dad/client case study page | Use proof in outreach |
| 13 | 90-day review, month 4 plan | Pipeline review and commitments |

# 4. Phase-by-Phase Daily Operating Rhythm

The spreadsheet contains a full 450-row day-by-day workflow. Because many rows intentionally repeat by phase, the clean manual version below shows the actual daily operating pattern to follow.

## Days 1-7: Foundation

| Time | Focus | Task | Owner | Output |
| --- | --- | --- | --- | --- |
| 9:00-10:30 | Website + Offer | Build or publish a Delko website asset: homepage, offer, CTA, proof placeholder, contact form, or analytics. | Keveen | Website closer to live |
| 10:30-12:00 | Dad Case Study | Capture or fix dad business foundation item: GBP, services, photos, reviews, quote process, or baseline screenshots. | Keveen | Proof asset created |
| 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script. | Keveen | Reusable template |
| 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire County or the North Shore. | Jack / Keveen | Prospects added |
| 3:00-4:00 | Outreach | Send or follow up with 5-10 warm or low-risk prospects using the audit offer. | Jack | Conversations started |

## Days 8-14: Case Study + Outreach Sprint

| Time | Focus | Task | Owner | Output |
| --- | --- | --- | --- | --- |
| 9:00-10:30 | Dad Case Study | Complete dad case study buildout: Google profile, photos, review request, quote form, lead tracker, or baseline proof. | Keveen | Case study foundation improved |
| 10:30-12:00 | Website Polish | Finalize service page, case study placeholder, audit form, Calendly/contact, mobile review, or tracking. | Keveen | Website more credible |
| 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking. | Keveen | Blocker removed |
| 2:00-3:00 | Audits | Create one short personalized audit for a qualified prospect. | Keveen | Audit ready |
| 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers. | Jack / Keveen | More conversations started |

## Days 15-30: Audit-Led Selling

| Time | Focus | Task | Owner | Output |
| --- | --- | --- | --- | --- |
| 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric. | Keveen | Proof update |
| 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps. | Keveen | Audit(s) ready |
| 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies. | Keveen | Sales asset improved |
| 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data. | Jack | Cleaner pipeline |
| 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach. | Jack / Keveen | Calls and replies |

## Days 31-60: Close + Deliver

| Time | Focus | Task | Owner | Output |
| --- | --- | --- | --- | --- |
| 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study tasks: GBP, website, review system, lead tracker, content, or reporting. | Keveen | Client/dad asset shipped |
| 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write a short progress note. | Keveen | Proof captured |
| 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda. | Both | Clear next actions |
| 2:00-3:00 | Outreach | Jack sends 8-15 new or follow-up touches; Keveen supports with specific audit insights. | Jack / Keveen | Pipeline stays alive |
| 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness. | Keveen | Delivery blocker removed |

## Days 61-90: Systemize + Scale

| Time | Focus | Task | Owner | Output |
| --- | --- | --- | --- | --- |
| 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content. | Keveen | Client work moved forward |
| 11:00-12:00 | Systems | Document the repeatable version of today's work as an SOP, checklist, template, or automation. | Keveen | System asset created |
| 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section. | Keveen | Sales proof improved |
| 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals. | Jack | Pipeline active |
| 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action. | Both | Decision made |

# 5. Website + Dad Case Study Checklist

This is the first proof engine. The goal is not a perfect brand launch. The goal is to show Delko can improve a real local business, document the before/after, and turn that proof into outreach.

## Website

| Priority | Task | Owner | Target Day | Est. Time | Proof / Output |
| --- | --- | --- | --- | --- | --- |
| High | Choose final domain and connect to site builder | Keveen | 1 | 30-60 min | Domain connected |
| High | Publish homepage with simple positioning and free audit CTA | Keveen | 3 | 2-3 hrs | Homepage live |
| High | Publish Services page around Local Presence Sprint and Local Growth System | Keveen | 4 | 1-2 hrs | Services page live |
| Medium | Add About page with local, personal, practical angle | Keveen | 5 | 45-90 min | About page live |
| High | Add Contact / Free Audit form | Keveen | 5 | 45-90 min | Form tested |
| High | Add placeholder Case Study page for dad's painting business | Keveen | 6 | 45 min | Case study page shell |
| Medium | Mobile review: headline, CTA, form, speed, navigation | Keveen | 6 | 30-45 min | Mobile passed |
| Medium | Add basic analytics/search console when ready | Keveen | 7 | 30-60 min | Tracking active |
| High | Final publish check: links, spelling, CTA, contact, trust | Keveen | 7 | 30 min | Website ready for outreach |

## Dad Case Study

| Priority | Task | Owner | Target Day | Est. Time | Proof / Output |
| --- | --- | --- | --- | --- | --- |
| High | Capture baseline screenshots: Google search, GBP, reviews, website/social, competitor examples | Keveen | 2 | 60-90 min | Before folder |
| High | Confirm services, service areas, phone, email, hours, photos, and strongest jobs | Keveen | 3 | 45-60 min | Business info sheet |
| High | Create or optimize Google Business Profile | Keveen | 5 | 1-2 hrs | GBP improved |
| High | Upload best photos and create before/after gallery folder | Keveen | 6 | 60-90 min | Visual proof folder |
| High | Create review request link, QR code, and text message script | Keveen | 7 | 45-60 min | Review system live |
| High | Create simple lead tracker or CRM sheet | Keveen | 8 | 45-60 min | Lead tracker live |
| Medium | Create quote request form or website contact flow | Keveen | 9 | 1-2 hrs | Lead capture live |
| Medium | Create 5 simple social/GBP posts using real work photos | Keveen | 10 | 1-2 hrs | First content batch |
| High | Write first case study draft: problem, what changed, early proof, next steps | Keveen | 14 | 60-90 min | Draft ready |

## Sales Asset

| Priority | Task | Owner | Target Day | Est. Time | Proof / Output |
| --- | --- | --- | --- | --- | --- |
| High | Finalize 1-page audit template | Keveen | 3 | 60 min | Reusable audit |
| High | Finalize discovery call script | Both | 7 | 45 min | Call flow ready |
| High | Finalize proposal template with 2 options | Keveen | 10 | 1-2 hrs | Proposal ready |
| Medium | Create pilot offer language for first 3 clients | Both | 12 | 30 min | Pilot script ready |

# 6. CRM + Scorecard System

The CRM tracks one thing: who needs the next touch. Every prospect should have a clear status and a clear next action.

| CRM Field | How to Use It |
| --- | --- |
| Business Name | Company name. |
| Industry | Vertical, such as painting, HVAC, roofing, salon, restaurant, med spa. |
| Location | Town or service area. |
| Owner / Contact | Decision-maker name when possible. |
| Email | Best email found. |
| Phone | Best phone number. |
| Website | Website URL. |
| Review Count | Google review count at time of audit. |
| Main Gap | Biggest issue: GBP, reviews, website, follow-up, content, or ads. |
| Offer Fit | Starter, Local Growth System, Growth Partner, or Not Fit. |
| Status | Current pipeline stage. |
| Last Touch | Most recent outreach/follow-up date. |

## Recommended CRM Statuses

| Status | Meaning |
| --- | --- |
| Researching | Prospect identified but not contacted yet. |
| Contacted | Initial DM, email, letter, call, or warm intro sent. |
| Replied | Prospect responded, but no call booked yet. |
| Audit Sent | Free audit or Loom sent. |
| Call Booked | Discovery call scheduled. |
| Proposal Sent | Proposal has been delivered or walkthrough is scheduled. |
| Closed Won | Client paid or signed. |
| Closed Lost | Not moving forward. Save reason. |
| Follow Up Later | Not now, but worth revisiting. |

## Weekly Scorecard

| Week | New Prospects | Outreach Sent | Replies | Audits Sent | Calls Booked | Proposals Sent | Clients Closed | MRR | Website Tasks Done | Dad Tasks Done | Main Bottleneck |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |  |

## 90-Day Scorecard Targets

| Metric | Target |
| --- | --- |
| New Prospects | 250 |
| Outreach Sent | 300 |
| Replies | 30 |
| Audits Sent | 20 |
| Calls Booked | 10 |
| Proposals Sent | 5 |
| Clients Closed | 3 |
| MRR | 5000 |
| Website Tasks Done | Website live by Day 7 |
| Dad Tasks Done | Dad case study draft by Day 14 |
| Main Bottleneck | Clear niche/offer |

# 7. Reference Rules

## Operating Principles

| Principle | Meaning | How It Shows Up |
| --- | --- | --- |
| 80/20 | Focus on the small set of actions that create clients and proof | Website, dad case study, audits, outreach, calls |
| Proof beats promises | Every client or test should produce before/after evidence | Screenshots, review count, calls, forms, GBP improvements |
| Simple beats fancy | Local owners care about calls, trust, reviews, and follow-up | Avoid jargon and sell clear outcomes |
| One owner per task | If both people own it, nobody owns it | Keveen owns delivery; Jack owns outreach |
| Outreach never stops | Pipeline today creates clients later | Minimum daily touches even during fulfillment |
| Start narrow | Begin with home services and painting-style businesses | Build one case study before expanding |
| Website matters | It is trust infrastructure, not a vanity project | Publish fast, improve from feedback |
| Learning is capped | Learn only what removes today's blocker | 90 minutes max in early phase |

## Partner Operating Lanes

| Role | Owner | Weekly Minimum | Scorecard Metric | Notes |
| --- | --- | --- | --- | --- |
| Sales / Outreach | Jack | 50-75 touches | Outreach Sent, Calls Booked | Jack owns volume and follow-up |
| Delivery / Systems | Keveen | 5-10 assets/tasks | Tasks Done, Website/Dad Progress | Keveen owns fulfillment quality |
| Strategy | Both | 1 weekly meeting | Decisions made | Keep offer simple |
| Case Studies | Keveen | 1 proof update/week | Proof captured | Dad's business first |
| Client Selection | Both | Review before closing | Fit score | Avoid bad clients early |

## Starting Offers

| Offer | Pitch | Core Deliverables | Price Logic |
| --- | --- | --- | --- |
| Starter Presence | Fix the basics so local customers trust you before they call | GBP cleanup, basic site fixes, review link, lead tracking | $750/mo or setup + $500/mo |
| Local Growth System | Improve website, Google presence, reviews, content, and follow-up | Landing page, local SEO, reviews, lead capture, follow-up, monthly report | $1,500/mo or setup + $1,000/mo |
| Pilot Offer | First 3 clients get reduced rate in exchange for documented case study if results are there | 90-day sprint with clear outcome tracking | Use to overcome no-case-study objection |

## Source Inputs Used to Build This Operating Plan

| Input Area | Source File | Used For |
| --- | --- | --- |
| Agency positioning, rulebook, packages, KPIs | Marketing Agency Brain OS.docx | Core offer, weekly scorecard, 80/20 operating logic |
| Roles and ownership | Delko_Partnership_Agreement_50-50.docx | Keveen/Jack lanes and 90-day review metrics |
| Original roadmap | 90 day plan.pdf | Condensed into action-first workflow |
| Sales system | Agency_Sales_System.docx | Home services focus, outreach, discovery, proposal sequence |
| AI search positioning | Brand Visibility in the AI search era.pdf | Future positioning layer, not first 14-day priority |
| Professional services playbook | BGC_Sales_Playbook.docx | Later expansion into law/financial advisors |

# Final Execution Reminder

The Rule That Keeps Delko Moving Do not let delivery stop outreach, and do not let learning replace conversations. If the week does not create proof, conversations, or a better system, the week was too passive.