## Dashboard
Delko 90-Day Operating Plan
Start Date | 2026-05-11 | KPI | Formula / Target | Current | Goal | Status
Current Day | 1 | Overall Task Progress | Done tasks / total tasks | 0% | 80%+ | Needs Work
Target by Day 14 | Website live + dad case study foundation + 50 qualified prospects | Website Launch Tasks Done | Website launch checklist | 0% | 100% by Day 7 | Open
Target by Day 30 | Website live, 100+ contacted, 3-5 discovery calls, 1 proposal | Dad Case Study Tasks Done | Case study checklist | 0% | 100% by Day 14 | Open
Target by Day 60 | 1-2 paying clients, dad case study active, $1.5K-$4.5K MRR | Prospects Added | CRM rows with business name | 0 | 50 by Day 14 | Build List
Target by Day 90 | 3-5 clients, first case study published, repeatable sales/delivery system | Outreach Sent | CRM rows marked Contacted or later | 0 | 100 by Day 30 | Keep Going
80/20 Rule | Every day must create proof, conversations, or a better system | Discovery Calls Booked | CRM status | 0 | 3-5 by Day 30 | Need Calls
|  | Clients Closed | CRM closed won | 0 | 3-5 by Day 90 | Pipeline
|  | Daily Non-Negotiables | Owner | Minimum | Why It Matters | Done Today?
|  | Update dad case study or client proof | Keveen | 60 minutes | Proof beats promises
|  | Add or clean prospects | Jack / Keveen | 5 businesses | Pipeline starts with qualified lists
|  | Send or follow up | Jack | 10 touches | Conversations create clients
|  | Build one system asset | Keveen | 1 template/SOP/checklist | Systems compound
|  | Review CRM | Both | 10 minutes | No leads fall through cracks
|  | Cap learning | Keveen | 90 minutes | Avoid hiding in research

## Daily Workflow
Day | Date | Week | Phase | Time Block | 80/20 Focus | Task | Owner | Output | If Done Early | Status | Notes
1 | 2026-05-11 | 1 | Foundation | 9:00-10:30 | Website + Offer | Build/publish Delko website asset for Day 1: homepage, offer, CTA, proof placeholder, contact form, or analytics | Keveen | Website closer to live | Move to dad case study baseline | Not Started
1 | 2026-05-11 | 1 | Foundation | 10:30-12:00 | Dad Case Study | Capture/fix dad business foundation item for Day 1: GBP, services, photos, reviews, quote process, or baseline screenshots | Keveen | Proof asset created | Turn into before/after screenshot | Not Started
1 | 2026-05-11 | 1 | Foundation | 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script | Keveen | Reusable template | Clean formatting and save in OS | Not Started
1 | 2026-05-11 | 1 | Foundation | 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire/North Shore | Jack / Keveen | Prospects added | Find owner name/contact | Not Started
1 | 2026-05-11 | 1 | Foundation | 3:00-4:00 | Outreach | Send/follow up with 5-10 warm or low-risk prospects using audit offer | Jack | Conversations started | Log CRM and prep next follow-up | Not Started
2 | 2026-05-12 | 1 | Foundation | 9:00-10:30 | Website + Offer | Build/publish Delko website asset for Day 2: homepage, offer, CTA, proof placeholder, contact form, or analytics | Keveen | Website closer to live | Move to dad case study baseline | Not Started
2 | 2026-05-12 | 1 | Foundation | 10:30-12:00 | Dad Case Study | Capture/fix dad business foundation item for Day 2: GBP, services, photos, reviews, quote process, or baseline screenshots | Keveen | Proof asset created | Turn into before/after screenshot | Not Started
2 | 2026-05-12 | 1 | Foundation | 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script | Keveen | Reusable template | Clean formatting and save in OS | Not Started
2 | 2026-05-12 | 1 | Foundation | 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire/North Shore | Jack / Keveen | Prospects added | Find owner name/contact | Not Started
2 | 2026-05-12 | 1 | Foundation | 3:00-4:00 | Outreach | Send/follow up with 5-10 warm or low-risk prospects using audit offer | Jack | Conversations started | Log CRM and prep next follow-up | Not Started
3 | 2026-05-13 | 1 | Foundation | 9:00-10:30 | Website + Offer | Build/publish Delko website asset for Day 3: homepage, offer, CTA, proof placeholder, contact form, or analytics | Keveen | Website closer to live | Move to dad case study baseline | Not Started
3 | 2026-05-13 | 1 | Foundation | 10:30-12:00 | Dad Case Study | Capture/fix dad business foundation item for Day 3: GBP, services, photos, reviews, quote process, or baseline screenshots | Keveen | Proof asset created | Turn into before/after screenshot | Not Started
3 | 2026-05-13 | 1 | Foundation | 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script | Keveen | Reusable template | Clean formatting and save in OS | Not Started
3 | 2026-05-13 | 1 | Foundation | 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire/North Shore | Jack / Keveen | Prospects added | Find owner name/contact | Not Started
3 | 2026-05-13 | 1 | Foundation | 3:00-4:00 | Outreach | Send/follow up with 5-10 warm or low-risk prospects using audit offer | Jack | Conversations started | Log CRM and prep next follow-up | Not Started
4 | 2026-05-14 | 1 | Foundation | 9:00-10:30 | Website + Offer | Build/publish Delko website asset for Day 4: homepage, offer, CTA, proof placeholder, contact form, or analytics | Keveen | Website closer to live | Move to dad case study baseline | Not Started
4 | 2026-05-14 | 1 | Foundation | 10:30-12:00 | Dad Case Study | Capture/fix dad business foundation item for Day 4: GBP, services, photos, reviews, quote process, or baseline screenshots | Keveen | Proof asset created | Turn into before/after screenshot | Not Started
4 | 2026-05-14 | 1 | Foundation | 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script | Keveen | Reusable template | Clean formatting and save in OS | Not Started
4 | 2026-05-14 | 1 | Foundation | 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire/North Shore | Jack / Keveen | Prospects added | Find owner name/contact | Not Started
4 | 2026-05-14 | 1 | Foundation | 3:00-4:00 | Outreach | Send/follow up with 5-10 warm or low-risk prospects using audit offer | Jack | Conversations started | Log CRM and prep next follow-up | Not Started
5 | 2026-05-15 | 1 | Foundation | 9:00-10:30 | Website + Offer | Build/publish Delko website asset for Day 5: homepage, offer, CTA, proof placeholder, contact form, or analytics | Keveen | Website closer to live | Move to dad case study baseline | Not Started
5 | 2026-05-15 | 1 | Foundation | 10:30-12:00 | Dad Case Study | Capture/fix dad business foundation item for Day 5: GBP, services, photos, reviews, quote process, or baseline screenshots | Keveen | Proof asset created | Turn into before/after screenshot | Not Started
5 | 2026-05-15 | 1 | Foundation | 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script | Keveen | Reusable template | Clean formatting and save in OS | Not Started
5 | 2026-05-15 | 1 | Foundation | 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire/North Shore | Jack / Keveen | Prospects added | Find owner name/contact | Not Started
5 | 2026-05-15 | 1 | Foundation | 3:00-4:00 | Outreach | Send/follow up with 5-10 warm or low-risk prospects using audit offer | Jack | Conversations started | Log CRM and prep next follow-up | Not Started
6 | 2026-05-16 | 1 | Foundation | 9:00-10:30 | Website + Offer | Build/publish Delko website asset for Day 6: homepage, offer, CTA, proof placeholder, contact form, or analytics | Keveen | Website closer to live | Move to dad case study baseline | Not Started
6 | 2026-05-16 | 1 | Foundation | 10:30-12:00 | Dad Case Study | Capture/fix dad business foundation item for Day 6: GBP, services, photos, reviews, quote process, or baseline screenshots | Keveen | Proof asset created | Turn into before/after screenshot | Not Started
6 | 2026-05-16 | 1 | Foundation | 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script | Keveen | Reusable template | Clean formatting and save in OS | Not Started
6 | 2026-05-16 | 1 | Foundation | 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire/North Shore | Jack / Keveen | Prospects added | Find owner name/contact | Not Started
6 | 2026-05-16 | 1 | Foundation | 3:00-4:00 | Outreach | Send/follow up with 5-10 warm or low-risk prospects using audit offer | Jack | Conversations started | Log CRM and prep next follow-up | Not Started
7 | 2026-05-17 | 1 | Foundation | 9:00-10:30 | Website + Offer | Build/publish Delko website asset for Day 7: homepage, offer, CTA, proof placeholder, contact form, or analytics | Keveen | Website closer to live | Move to dad case study baseline | Not Started
7 | 2026-05-17 | 1 | Foundation | 10:30-12:00 | Dad Case Study | Capture/fix dad business foundation item for Day 7: GBP, services, photos, reviews, quote process, or baseline screenshots | Keveen | Proof asset created | Turn into before/after screenshot | Not Started
7 | 2026-05-17 | 1 | Foundation | 1:00-2:00 | System Asset | Create one reusable asset: audit template, proposal outline, CRM field, checklist, or sales script | Keveen | Reusable template | Clean formatting and save in OS | Not Started
7 | 2026-05-17 | 1 | Foundation | 2:00-3:00 | Prospect List | Add and score 5-10 home service prospects in Berkshire/North Shore | Jack / Keveen | Prospects added | Find owner name/contact | Not Started
7 | 2026-05-17 | 1 | Foundation | 3:00-4:00 | Outreach | Send/follow up with 5-10 warm or low-risk prospects using audit offer | Jack | Conversations started | Log CRM and prep next follow-up | Not Started
8 | 2026-05-18 | 2 | Foundation | 9:00-10:30 | Dad Case Study | Complete dad case study buildout item for Day 8: Google profile, photos, review request, quote form, lead tracker, or basic follow-up | Keveen | Visible improvement | Document before/after | Not Started
8 | 2026-05-18 | 2 | Foundation | 10:30-12:00 | Website Polish | Finalize website piece: service page, case study placeholder, audit form, Calendly/contact, mobile review, or publish checks | Keveen | Website live/polished | Create screenshot proof | Not Started
8 | 2026-05-18 | 2 | Foundation | 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking | Keveen | One practical note | Turn note into checklist item | Not Started
8 | 2026-05-18 | 2 | Foundation | 2:00-3:00 | Audits | Create 1 short personalized audit for a qualified prospect | Keveen | Audit ready | Make Loom or screenshot | Not Started
8 | 2026-05-18 | 2 | Foundation | 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers | Jack / Keveen | CRM updated | Schedule follow-ups | Not Started
9 | 2026-05-19 | 2 | Foundation | 9:00-10:30 | Dad Case Study | Complete dad case study buildout item for Day 9: Google profile, photos, review request, quote form, lead tracker, or basic follow-up | Keveen | Visible improvement | Document before/after | Not Started
9 | 2026-05-19 | 2 | Foundation | 10:30-12:00 | Website Polish | Finalize website piece: service page, case study placeholder, audit form, Calendly/contact, mobile review, or publish checks | Keveen | Website live/polished | Create screenshot proof | Not Started
9 | 2026-05-19 | 2 | Foundation | 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking | Keveen | One practical note | Turn note into checklist item | Not Started
9 | 2026-05-19 | 2 | Foundation | 2:00-3:00 | Audits | Create 1 short personalized audit for a qualified prospect | Keveen | Audit ready | Make Loom or screenshot | Not Started
9 | 2026-05-19 | 2 | Foundation | 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers | Jack / Keveen | CRM updated | Schedule follow-ups | Not Started
10 | 2026-05-20 | 2 | Foundation | 9:00-10:30 | Dad Case Study | Complete dad case study buildout item for Day 10: Google profile, photos, review request, quote form, lead tracker, or basic follow-up | Keveen | Visible improvement | Document before/after | Not Started
10 | 2026-05-20 | 2 | Foundation | 10:30-12:00 | Website Polish | Finalize website piece: service page, case study placeholder, audit form, Calendly/contact, mobile review, or publish checks | Keveen | Website live/polished | Create screenshot proof | Not Started
10 | 2026-05-20 | 2 | Foundation | 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking | Keveen | One practical note | Turn note into checklist item | Not Started
10 | 2026-05-20 | 2 | Foundation | 2:00-3:00 | Audits | Create 1 short personalized audit for a qualified prospect | Keveen | Audit ready | Make Loom or screenshot | Not Started
10 | 2026-05-20 | 2 | Foundation | 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers | Jack / Keveen | CRM updated | Schedule follow-ups | Not Started
11 | 2026-05-21 | 2 | Foundation | 9:00-10:30 | Dad Case Study | Complete dad case study buildout item for Day 11: Google profile, photos, review request, quote form, lead tracker, or basic follow-up | Keveen | Visible improvement | Document before/after | Not Started
11 | 2026-05-21 | 2 | Foundation | 10:30-12:00 | Website Polish | Finalize website piece: service page, case study placeholder, audit form, Calendly/contact, mobile review, or publish checks | Keveen | Website live/polished | Create screenshot proof | Not Started
11 | 2026-05-21 | 2 | Foundation | 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking | Keveen | One practical note | Turn note into checklist item | Not Started
11 | 2026-05-21 | 2 | Foundation | 2:00-3:00 | Audits | Create 1 short personalized audit for a qualified prospect | Keveen | Audit ready | Make Loom or screenshot | Not Started
11 | 2026-05-21 | 2 | Foundation | 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers | Jack / Keveen | CRM updated | Schedule follow-ups | Not Started
12 | 2026-05-22 | 2 | Foundation | 9:00-10:30 | Dad Case Study | Complete dad case study buildout item for Day 12: Google profile, photos, review request, quote form, lead tracker, or basic follow-up | Keveen | Visible improvement | Document before/after | Not Started
12 | 2026-05-22 | 2 | Foundation | 10:30-12:00 | Website Polish | Finalize website piece: service page, case study placeholder, audit form, Calendly/contact, mobile review, or publish checks | Keveen | Website live/polished | Create screenshot proof | Not Started
12 | 2026-05-22 | 2 | Foundation | 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking | Keveen | One practical note | Turn note into checklist item | Not Started
12 | 2026-05-22 | 2 | Foundation | 2:00-3:00 | Audits | Create 1 short personalized audit for a qualified prospect | Keveen | Audit ready | Make Loom or screenshot | Not Started
12 | 2026-05-22 | 2 | Foundation | 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers | Jack / Keveen | CRM updated | Schedule follow-ups | Not Started
13 | 2026-05-23 | 2 | Foundation | 9:00-10:30 | Dad Case Study | Complete dad case study buildout item for Day 13: Google profile, photos, review request, quote form, lead tracker, or basic follow-up | Keveen | Visible improvement | Document before/after | Not Started
13 | 2026-05-23 | 2 | Foundation | 10:30-12:00 | Website Polish | Finalize website piece: service page, case study placeholder, audit form, Calendly/contact, mobile review, or publish checks | Keveen | Website live/polished | Create screenshot proof | Not Started
13 | 2026-05-23 | 2 | Foundation | 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking | Keveen | One practical note | Turn note into checklist item | Not Started
13 | 2026-05-23 | 2 | Foundation | 2:00-3:00 | Audits | Create 1 short personalized audit for a qualified prospect | Keveen | Audit ready | Make Loom or screenshot | Not Started
13 | 2026-05-23 | 2 | Foundation | 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers | Jack / Keveen | CRM updated | Schedule follow-ups | Not Started
14 | 2026-05-24 | 2 | Foundation | 9:00-10:30 | Dad Case Study | Complete dad case study buildout item for Day 14: Google profile, photos, review request, quote form, lead tracker, or basic follow-up | Keveen | Visible improvement | Document before/after | Not Started
14 | 2026-05-24 | 2 | Foundation | 10:30-12:00 | Website Polish | Finalize website piece: service page, case study placeholder, audit form, Calendly/contact, mobile review, or publish checks | Keveen | Website live/polished | Create screenshot proof | Not Started
14 | 2026-05-24 | 2 | Foundation | 1:00-2:00 | Learning | Learn only the specific skill needed today: GBP, local SEO audit, basic CRO, reviews, or lead tracking | Keveen | One practical note | Turn note into checklist item | Not Started
14 | 2026-05-24 | 2 | Foundation | 2:00-3:00 | Audits | Create 1 short personalized audit for a qualified prospect | Keveen | Audit ready | Make Loom or screenshot | Not Started
14 | 2026-05-24 | 2 | Foundation | 3:00-4:00 | Outreach | Jack sends 10-20 touches; Keveen sends 3-5 personalized audit offers | Jack / Keveen | CRM updated | Schedule follow-ups | Not Started
15 | 2026-05-25 | 3 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
15 | 2026-05-25 | 3 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
15 | 2026-05-25 | 3 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
15 | 2026-05-25 | 3 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
15 | 2026-05-25 | 3 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
16 | 2026-05-26 | 3 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
16 | 2026-05-26 | 3 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
16 | 2026-05-26 | 3 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
16 | 2026-05-26 | 3 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
16 | 2026-05-26 | 3 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
17 | 2026-05-27 | 3 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
17 | 2026-05-27 | 3 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
17 | 2026-05-27 | 3 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
17 | 2026-05-27 | 3 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
17 | 2026-05-27 | 3 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
18 | 2026-05-28 | 3 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
18 | 2026-05-28 | 3 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
18 | 2026-05-28 | 3 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
18 | 2026-05-28 | 3 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
18 | 2026-05-28 | 3 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
19 | 2026-05-29 | 3 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
19 | 2026-05-29 | 3 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
19 | 2026-05-29 | 3 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
19 | 2026-05-29 | 3 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
19 | 2026-05-29 | 3 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
20 | 2026-05-30 | 3 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
20 | 2026-05-30 | 3 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
20 | 2026-05-30 | 3 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
20 | 2026-05-30 | 3 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
20 | 2026-05-30 | 3 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
21 | 2026-05-31 | 3 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
21 | 2026-05-31 | 3 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
21 | 2026-05-31 | 3 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
21 | 2026-05-31 | 3 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
21 | 2026-05-31 | 3 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
22 | 2026-06-01 | 4 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
22 | 2026-06-01 | 4 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
22 | 2026-06-01 | 4 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
22 | 2026-06-01 | 4 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
22 | 2026-06-01 | 4 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
23 | 2026-06-02 | 4 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
23 | 2026-06-02 | 4 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
23 | 2026-06-02 | 4 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
23 | 2026-06-02 | 4 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
23 | 2026-06-02 | 4 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
24 | 2026-06-03 | 4 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
24 | 2026-06-03 | 4 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
24 | 2026-06-03 | 4 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
24 | 2026-06-03 | 4 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
24 | 2026-06-03 | 4 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
25 | 2026-06-04 | 4 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
25 | 2026-06-04 | 4 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
25 | 2026-06-04 | 4 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
25 | 2026-06-04 | 4 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
25 | 2026-06-04 | 4 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
26 | 2026-06-05 | 4 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
26 | 2026-06-05 | 4 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
26 | 2026-06-05 | 4 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
26 | 2026-06-05 | 4 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
26 | 2026-06-05 | 4 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
27 | 2026-06-06 | 4 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
27 | 2026-06-06 | 4 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
27 | 2026-06-06 | 4 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
27 | 2026-06-06 | 4 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
27 | 2026-06-06 | 4 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
28 | 2026-06-07 | 4 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
28 | 2026-06-07 | 4 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
28 | 2026-06-07 | 4 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
28 | 2026-06-07 | 4 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
28 | 2026-06-07 | 4 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
29 | 2026-06-08 | 5 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
29 | 2026-06-08 | 5 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
29 | 2026-06-08 | 5 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
29 | 2026-06-08 | 5 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
29 | 2026-06-08 | 5 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
30 | 2026-06-09 | 5 | Outreach + Calls | 9:00-10:00 | Dad Proof / Website | Update dad case study or website proof section with one visible improvement or metric | Keveen | Proof updated | Create social/proposal snippet | Not Started
30 | 2026-06-09 | 5 | Outreach + Calls | 10:00-11:00 | Audit Production | Build or refine 1-2 prospect audits using Google profile, website, reviews, and follow-up gaps | Keveen | Audit sent-ready | Record 3-min Loom | Not Started
30 | 2026-06-09 | 5 | Outreach + Calls | 11:00-12:00 | Sales Support | Prep call notes, proposal language, or objection response from actual replies | Keveen | Sales asset updated | Practice call flow | Not Started
30 | 2026-06-09 | 5 | Outreach + Calls | 1:00-2:00 | Prospecting | Add 5-10 new qualified prospects or clean owner/contact data | Jack | Pipeline expanded | Prioritize top 5 | Not Started
30 | 2026-06-09 | 5 | Outreach + Calls | 2:00-4:00 | Outreach + Follow-Up | Jack sends/follows up with 10-20 prospects; Keveen joins calls or sends high-personalization outreach | Jack / Keveen | Replies/calls | Book calendar slots | Not Started
31 | 2026-06-10 | 5 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
31 | 2026-06-10 | 5 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
31 | 2026-06-10 | 5 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
31 | 2026-06-10 | 5 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
31 | 2026-06-10 | 5 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
32 | 2026-06-11 | 5 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
32 | 2026-06-11 | 5 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
32 | 2026-06-11 | 5 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
32 | 2026-06-11 | 5 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
32 | 2026-06-11 | 5 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
33 | 2026-06-12 | 5 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
33 | 2026-06-12 | 5 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
33 | 2026-06-12 | 5 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
33 | 2026-06-12 | 5 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
33 | 2026-06-12 | 5 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
34 | 2026-06-13 | 5 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
34 | 2026-06-13 | 5 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
34 | 2026-06-13 | 5 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
34 | 2026-06-13 | 5 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
34 | 2026-06-13 | 5 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
35 | 2026-06-14 | 5 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
35 | 2026-06-14 | 5 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
35 | 2026-06-14 | 5 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
35 | 2026-06-14 | 5 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
35 | 2026-06-14 | 5 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
36 | 2026-06-15 | 6 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
36 | 2026-06-15 | 6 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
36 | 2026-06-15 | 6 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
36 | 2026-06-15 | 6 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
36 | 2026-06-15 | 6 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
37 | 2026-06-16 | 6 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
37 | 2026-06-16 | 6 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
37 | 2026-06-16 | 6 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
37 | 2026-06-16 | 6 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
37 | 2026-06-16 | 6 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
38 | 2026-06-17 | 6 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
38 | 2026-06-17 | 6 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
38 | 2026-06-17 | 6 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
38 | 2026-06-17 | 6 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
38 | 2026-06-17 | 6 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
39 | 2026-06-18 | 6 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
39 | 2026-06-18 | 6 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
39 | 2026-06-18 | 6 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
39 | 2026-06-18 | 6 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
39 | 2026-06-18 | 6 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
40 | 2026-06-19 | 6 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
40 | 2026-06-19 | 6 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
40 | 2026-06-19 | 6 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
40 | 2026-06-19 | 6 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
40 | 2026-06-19 | 6 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
41 | 2026-06-20 | 6 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
41 | 2026-06-20 | 6 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
41 | 2026-06-20 | 6 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
41 | 2026-06-20 | 6 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
41 | 2026-06-20 | 6 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
42 | 2026-06-21 | 6 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
42 | 2026-06-21 | 6 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
42 | 2026-06-21 | 6 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
42 | 2026-06-21 | 6 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
42 | 2026-06-21 | 6 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
43 | 2026-06-22 | 7 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
43 | 2026-06-22 | 7 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
43 | 2026-06-22 | 7 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
43 | 2026-06-22 | 7 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
43 | 2026-06-22 | 7 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
44 | 2026-06-23 | 7 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
44 | 2026-06-23 | 7 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
44 | 2026-06-23 | 7 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
44 | 2026-06-23 | 7 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
44 | 2026-06-23 | 7 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
45 | 2026-06-24 | 7 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
45 | 2026-06-24 | 7 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
45 | 2026-06-24 | 7 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
45 | 2026-06-24 | 7 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
45 | 2026-06-24 | 7 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
46 | 2026-06-25 | 7 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
46 | 2026-06-25 | 7 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
46 | 2026-06-25 | 7 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
46 | 2026-06-25 | 7 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
46 | 2026-06-25 | 7 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
47 | 2026-06-26 | 7 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
47 | 2026-06-26 | 7 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
47 | 2026-06-26 | 7 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
47 | 2026-06-26 | 7 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
47 | 2026-06-26 | 7 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
48 | 2026-06-27 | 7 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
48 | 2026-06-27 | 7 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
48 | 2026-06-27 | 7 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
48 | 2026-06-27 | 7 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
48 | 2026-06-27 | 7 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
49 | 2026-06-28 | 7 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
49 | 2026-06-28 | 7 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
49 | 2026-06-28 | 7 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
49 | 2026-06-28 | 7 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
49 | 2026-06-28 | 7 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
50 | 2026-06-29 | 8 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
50 | 2026-06-29 | 8 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
50 | 2026-06-29 | 8 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
50 | 2026-06-29 | 8 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
50 | 2026-06-29 | 8 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
51 | 2026-06-30 | 8 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
51 | 2026-06-30 | 8 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
51 | 2026-06-30 | 8 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
51 | 2026-06-30 | 8 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
51 | 2026-06-30 | 8 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
52 | 2026-07-01 | 8 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
52 | 2026-07-01 | 8 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
52 | 2026-07-01 | 8 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
52 | 2026-07-01 | 8 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
52 | 2026-07-01 | 8 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
53 | 2026-07-02 | 8 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
53 | 2026-07-02 | 8 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
53 | 2026-07-02 | 8 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
53 | 2026-07-02 | 8 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
53 | 2026-07-02 | 8 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
54 | 2026-07-03 | 8 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
54 | 2026-07-03 | 8 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
54 | 2026-07-03 | 8 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
54 | 2026-07-03 | 8 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
54 | 2026-07-03 | 8 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
55 | 2026-07-04 | 8 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
55 | 2026-07-04 | 8 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
55 | 2026-07-04 | 8 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
55 | 2026-07-04 | 8 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
55 | 2026-07-04 | 8 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
56 | 2026-07-05 | 8 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
56 | 2026-07-05 | 8 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
56 | 2026-07-05 | 8 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
56 | 2026-07-05 | 8 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
56 | 2026-07-05 | 8 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
57 | 2026-07-06 | 9 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
57 | 2026-07-06 | 9 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
57 | 2026-07-06 | 9 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
57 | 2026-07-06 | 9 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
57 | 2026-07-06 | 9 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
58 | 2026-07-07 | 9 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
58 | 2026-07-07 | 9 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
58 | 2026-07-07 | 9 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
58 | 2026-07-07 | 9 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
58 | 2026-07-07 | 9 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
59 | 2026-07-08 | 9 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
59 | 2026-07-08 | 9 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
59 | 2026-07-08 | 9 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
59 | 2026-07-08 | 9 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
59 | 2026-07-08 | 9 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
60 | 2026-07-09 | 9 | Close + Deliver | 9:00-11:00 | Client/Dad Delivery | Fulfill active client or dad case study task: GBP, website, review system, lead tracker, content, or report | Keveen | Client result | Document SOP step | Not Started
60 | 2026-07-09 | 9 | Close + Deliver | 11:00-12:00 | Reporting / Proof | Capture before/after screenshots, update dashboard, or write short progress note | Keveen | Proof captured | Add to case study | Not Started
60 | 2026-07-09 | 9 | Close + Deliver | 1:00-2:00 | Pipeline Review | Review CRM, prioritize follow-ups, prep proposal/call agenda | Both | Next actions clear | Assign owner | Not Started
60 | 2026-07-09 | 9 | Close + Deliver | 2:00-3:00 | Outreach | Jack sends 8-15 new/follow-up touches; Keveen supports with specific audit insights | Jack / Keveen | Pipeline active | Send referral ask | Not Started
60 | 2026-07-09 | 9 | Close + Deliver | 3:00-4:00 | Learning / Fix Gap | Learn only the thing blocking fulfillment: analytics, GBP, local SEO, forms, CRM, or ads readiness | Keveen | Blocker removed | Update SOP | Not Started
61 | 2026-07-10 | 9 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
61 | 2026-07-10 | 9 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
61 | 2026-07-10 | 9 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
61 | 2026-07-10 | 9 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
61 | 2026-07-10 | 9 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
62 | 2026-07-11 | 9 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
62 | 2026-07-11 | 9 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
62 | 2026-07-11 | 9 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
62 | 2026-07-11 | 9 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
62 | 2026-07-11 | 9 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
63 | 2026-07-12 | 9 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
63 | 2026-07-12 | 9 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
63 | 2026-07-12 | 9 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
63 | 2026-07-12 | 9 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
63 | 2026-07-12 | 9 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
64 | 2026-07-13 | 10 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
64 | 2026-07-13 | 10 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
64 | 2026-07-13 | 10 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
64 | 2026-07-13 | 10 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
64 | 2026-07-13 | 10 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
65 | 2026-07-14 | 10 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
65 | 2026-07-14 | 10 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
65 | 2026-07-14 | 10 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
65 | 2026-07-14 | 10 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
65 | 2026-07-14 | 10 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
66 | 2026-07-15 | 10 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
66 | 2026-07-15 | 10 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
66 | 2026-07-15 | 10 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
66 | 2026-07-15 | 10 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
66 | 2026-07-15 | 10 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
67 | 2026-07-16 | 10 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
67 | 2026-07-16 | 10 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
67 | 2026-07-16 | 10 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
67 | 2026-07-16 | 10 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
67 | 2026-07-16 | 10 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
68 | 2026-07-17 | 10 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
68 | 2026-07-17 | 10 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
68 | 2026-07-17 | 10 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
68 | 2026-07-17 | 10 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
68 | 2026-07-17 | 10 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
69 | 2026-07-18 | 10 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
69 | 2026-07-18 | 10 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
69 | 2026-07-18 | 10 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
69 | 2026-07-18 | 10 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
69 | 2026-07-18 | 10 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
70 | 2026-07-19 | 10 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
70 | 2026-07-19 | 10 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
70 | 2026-07-19 | 10 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
70 | 2026-07-19 | 10 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
70 | 2026-07-19 | 10 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
71 | 2026-07-20 | 11 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
71 | 2026-07-20 | 11 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
71 | 2026-07-20 | 11 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
71 | 2026-07-20 | 11 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
71 | 2026-07-20 | 11 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
72 | 2026-07-21 | 11 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
72 | 2026-07-21 | 11 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
72 | 2026-07-21 | 11 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
72 | 2026-07-21 | 11 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
72 | 2026-07-21 | 11 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
73 | 2026-07-22 | 11 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
73 | 2026-07-22 | 11 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
73 | 2026-07-22 | 11 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
73 | 2026-07-22 | 11 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
73 | 2026-07-22 | 11 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
74 | 2026-07-23 | 11 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
74 | 2026-07-23 | 11 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
74 | 2026-07-23 | 11 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
74 | 2026-07-23 | 11 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
74 | 2026-07-23 | 11 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
75 | 2026-07-24 | 11 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
75 | 2026-07-24 | 11 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
75 | 2026-07-24 | 11 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
75 | 2026-07-24 | 11 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
75 | 2026-07-24 | 11 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
76 | 2026-07-25 | 11 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
76 | 2026-07-25 | 11 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
76 | 2026-07-25 | 11 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
76 | 2026-07-25 | 11 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
76 | 2026-07-25 | 11 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
77 | 2026-07-26 | 11 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
77 | 2026-07-26 | 11 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
77 | 2026-07-26 | 11 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
77 | 2026-07-26 | 11 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
77 | 2026-07-26 | 11 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
78 | 2026-07-27 | 12 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
78 | 2026-07-27 | 12 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
78 | 2026-07-27 | 12 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
78 | 2026-07-27 | 12 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
78 | 2026-07-27 | 12 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
79 | 2026-07-28 | 12 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
79 | 2026-07-28 | 12 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
79 | 2026-07-28 | 12 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
79 | 2026-07-28 | 12 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
79 | 2026-07-28 | 12 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
80 | 2026-07-29 | 12 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
80 | 2026-07-29 | 12 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
80 | 2026-07-29 | 12 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
80 | 2026-07-29 | 12 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
80 | 2026-07-29 | 12 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
81 | 2026-07-30 | 12 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
81 | 2026-07-30 | 12 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
81 | 2026-07-30 | 12 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
81 | 2026-07-30 | 12 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
81 | 2026-07-30 | 12 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
82 | 2026-07-31 | 12 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
82 | 2026-07-31 | 12 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
82 | 2026-07-31 | 12 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
82 | 2026-07-31 | 12 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
82 | 2026-07-31 | 12 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
83 | 2026-08-01 | 12 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
83 | 2026-08-01 | 12 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
83 | 2026-08-01 | 12 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
83 | 2026-08-01 | 12 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
83 | 2026-08-01 | 12 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
84 | 2026-08-02 | 12 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
84 | 2026-08-02 | 12 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
84 | 2026-08-02 | 12 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
84 | 2026-08-02 | 12 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
84 | 2026-08-02 | 12 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
85 | 2026-08-03 | 13 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
85 | 2026-08-03 | 13 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
85 | 2026-08-03 | 13 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
85 | 2026-08-03 | 13 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
85 | 2026-08-03 | 13 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
86 | 2026-08-04 | 13 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
86 | 2026-08-04 | 13 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
86 | 2026-08-04 | 13 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
86 | 2026-08-04 | 13 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
86 | 2026-08-04 | 13 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
87 | 2026-08-05 | 13 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
87 | 2026-08-05 | 13 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
87 | 2026-08-05 | 13 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
87 | 2026-08-05 | 13 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
87 | 2026-08-05 | 13 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
88 | 2026-08-06 | 13 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
88 | 2026-08-06 | 13 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
88 | 2026-08-06 | 13 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
88 | 2026-08-06 | 13 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
88 | 2026-08-06 | 13 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
89 | 2026-08-07 | 13 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
89 | 2026-08-07 | 13 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
89 | 2026-08-07 | 13 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
89 | 2026-08-07 | 13 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
89 | 2026-08-07 | 13 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started
90 | 2026-08-08 | 13 | Systemize + Scale | 9:00-11:00 | Client Delivery | Serve current clients first: reporting, optimization, website fixes, review system, lead tracking, or content calendar | Keveen | Retention/proof | Delegate or SOP | Not Started
90 | 2026-08-08 | 13 | Systemize + Scale | 11:00-12:00 | Systems | Document the repeatable version of today's work as SOP, checklist, template, or automation | Keveen | System improved | Add to SOP backlog | Not Started
90 | 2026-08-08 | 13 | Systemize + Scale | 1:00-2:00 | Proof / Case Study | Update case study, testimonial request, performance snapshot, or website proof section | Keveen | Sales proof | Post or reuse in proposal | Not Started
90 | 2026-08-08 | 13 | Systemize + Scale | 2:00-3:00 | Sales Pipeline | Jack reviews pipeline, follows up with warm leads, books calls, or asks for referrals | Jack | Next call/proposal | Segment leads | Not Started
90 | 2026-08-08 | 13 | Systemize + Scale | 3:00-4:00 | Strategic Review | Review scorecard, bottleneck, pricing, niche signals, and next best action | Both | Better decision | Update next week priorities | Not Started

## Weekly Plan
Week | Days | Theme | 80/20 Priority | Keveen Focus | Jack Focus | Must Ship | Success Metric | Decision Gate
1 | 1-7 | Foundation + website launch | Publish credible website and start dad case study | Website, offer, audit template, dad baseline | Prospect list and first warm messages | Website live, audit template, CRM live | 25 prospects, 5 outreach, dad baseline captured | Is the offer simple enough to explain?
2 | 8-14 | Case study + outreach sprint | Create proof and start real conversations | Dad GBP/review/lead system, 5 audits | 20-30 outreach touches, follow-ups | Dad foundation live, 50 qualified prospects | 50 prospects, 10 audits, 2 calls booked | Are owners responding to the audit angle?
3 | 15-21 | Audit-led selling | Turn audits into calls | Audit improvements, proposal template, call support | Outreach/follow-up/call booking | 3-5 personalized audits | 100 total touches, 3 calls booked | Which vertical has strongest pull?
4 | 22-30 | First proposals | Use owner language to sell foundation package | Proposal + dad progress snapshot | Book calls, handle follow-ups | 1-2 proposals | 1 proposal sent, 1 serious buyer | Do we need a lower-friction pilot?
5 | 31-37 | Close first client | Move from conversations to paid pilot | Refine offer, prepare onboarding | Close, follow up, referrals | Pilot offer + onboarding checklist | 1 signed pilot or proposal in review | What objection repeats most?
6 | 38-45 | Client delivery begins | Deliver first result fast | GBP, website, reviews, tracking | Keep pipeline warm | Client week 1 report | 1 client live, 100+ total prospects | Is delivery taking too long?
7 | 46-52 | Proof building | Capture before/after and early wins | Client/dad reporting, SOPs | More outreach and referrals | Before/after proof folder | 2 active opportunities | What tasks can be templated?
8 | 53-60 | Second client push | Repeat what worked | Fulfillment + report system | Calls/proposals | Monthly report template | 1-2 clients, $1.5K-$4.5K MRR | Which package sells easiest?
9 | 61-67 | Optimize delivery | Make client work repeatable | SOPs, dashboards, case study draft | Outreach 5-10/day | Delivery SOP v1 | 2-3 clients/proposals | Are we ready to raise price?
10 | 68-75 | Scale outreach | Keep pipeline alive while delivering | Quality control and reports | Cold/warm/referral campaigns | Referral ask system | 3 active sales conversations | Do we need contractor support?
11 | 76-82 | Systemize | Turn recurring work into SOPs | SOP library, client welcome kit | Referral and nurture | 5 core SOPs | Delivery time reduced | What should we stop offering?
12 | 83-87 | Case study publish | Turn proof into sales asset | Dad/client case study page | Use proof in outreach | Case study live | 1 case study + testimonial request | Can proof support higher pricing?
13 | 88-90 | Review + next quarter | Decide niche, offer, roles, pricing | 90-day review, month 4 plan | Pipeline review and commitments | Month 4 plan | 3-5 clients target or clear bottleneck | Scale, niche, or reset?

## Website Case Study
Category | Priority | Task | Status | Owner | Target Day | Estimated Time | Proof / Output | Notes
Website | High | Choose final domain and connect to site builder | Not Started | Keveen | 1 | 30-60 min | Domain connected
Website | High | Publish homepage with simple positioning and free audit CTA | Not Started | Keveen | 3 | 2-3 hrs | Homepage live
Website | High | Publish Services page around Local Presence Sprint and Local Growth System | Not Started | Keveen | 4 | 1-2 hrs | Services page live
Website | Medium | Add About page with local, personal, practical angle | Not Started | Keveen | 5 | 45-90 min | About page live
Website | High | Add Contact / Free Audit form | Not Started | Keveen | 5 | 45-90 min | Form tested
Website | High | Add placeholder Case Study page for dad’s painting business | Not Started | Keveen | 6 | 45 min | Case study page shell
Website | Medium | Mobile review: headline, CTA, form, speed, navigation | Not Started | Keveen | 6 | 30-45 min | Mobile passed
Website | Medium | Add basic analytics/search console when ready | Not Started | Keveen | 7 | 30-60 min | Tracking active
Website | High | Final publish check: links, spelling, CTA, contact, trust | Not Started | Keveen | 7 | 30 min | Website ready for outreach
Dad Case Study | High | Capture baseline screenshots: Google search, GBP, reviews, website/social, competitor examples | Not Started | Keveen | 2 | 60-90 min | Before folder
Dad Case Study | High | Confirm services, service areas, phone, email, hours, photos, and strongest jobs | Not Started | Keveen | 3 | 45-60 min | Business info sheet
Dad Case Study | High | Create or optimize Google Business Profile | Not Started | Keveen | 5 | 1-2 hrs | GBP improved
Dad Case Study | High | Upload best photos and create before/after gallery folder | Not Started | Keveen | 6 | 60-90 min | Visual proof folder
Dad Case Study | High | Create review request link, QR code, and text message script | Not Started | Keveen | 7 | 45-60 min | Review system live
Dad Case Study | High | Create simple lead tracker or CRM sheet | Not Started | Keveen | 8 | 45-60 min | Lead tracker live
Dad Case Study | Medium | Create quote request form or website contact flow | Not Started | Keveen | 9 | 1-2 hrs | Lead capture live
Dad Case Study | Medium | Create 5 simple social/GBP posts using real work photos | Not Started | Keveen | 10 | 1-2 hrs | First content batch
Dad Case Study | High | Write first case study draft: problem, what changed, early proof, next steps | Not Started | Keveen | 14 | 60-90 min | Draft ready
Sales Asset | High | Finalize 1-page audit template | Not Started | Keveen | 3 | 60 min | Reusable audit
Sales Asset | High | Finalize discovery call script | Not Started | Both | 7 | 45 min | Call flow ready
Sales Asset | High | Finalize proposal template with 2 options | Not Started | Keveen | 10 | 1-2 hrs | Proposal ready
Sales Asset | Medium | Create pilot offer language for first 3 clients | Not Started | Both | 12 | 30 min | Pilot script ready

## CRM
Business Name | Industry | Location | Owner / Contact | Email | Phone | Website | Review Count | Main Gap | Offer Fit | Status | Last Touch | Next Follow-Up | Owner | Estimated Value | Notes

## Scorecard
Week | New Prospects | Outreach Sent | Replies | Audits Sent | Calls Booked | Proposals Sent | Clients Closed | MRR | Website Tasks Done | Dad Tasks Done | Main Bottleneck | Next Week Priority
1
2
3
4
5
6
7
8
9
10
11
12
13
90-Day Targets | 250 | 300 | 30 | 20 | 10 | 5 | 3 | 5000 | Website live by Day 7 | Dad case study draft by Day 14 | Clear niche/offer | Month 4 plan
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Reference
Operating Reference
Principle | Meaning | How It Shows Up
80/20 | Focus on the small set of actions that create clients and proof | Website, dad case study, audits, outreach, calls
Proof beats promises | Every client or test should produce before/after evidence | Screenshots, review count, calls, forms, GBP improvements
Simple beats fancy | Local owners care about calls, trust, reviews, and follow-up | Avoid jargon and sell clear outcomes
One owner per task | If both people own it, nobody owns it | Keveen owns delivery; Jack owns outreach
Outreach never stops | Pipeline today creates clients later | Minimum daily touches even during fulfillment
Start narrow | Begin with home services and painting-style businesses | Build one case study before expanding
Website matters | It is trust infrastructure, not a vanity project | Publish fast, improve from feedback
Learning is capped | Learn only what removes today’s blocker | 90 minutes max in early phase
Role | Primary Owner | Weekly Minimum | Scorecard Metric | Notes
Sales / Outreach | Jack | 50-75 touches | Outreach Sent, Calls Booked | Jack owns volume and follow-up
Delivery / Systems | Keveen | 5-10 assets/tasks | Tasks Done, Website/Dad Progress | Keveen owns fulfillment quality
Strategy | Both | 1 weekly meeting | Decisions made | Keep offer simple
Case Studies | Keveen | 1 proof update/week | Proof captured | Dad’s business first
Client Selection | Both | Review before closing | Fit score | Avoid bad clients early
Starting Offer | One-Sentence Pitch | Core Deliverables | Starting Price Logic
Starter Presence | Fix the basics so local customers trust you before they call | GBP cleanup, basic site fixes, review link, lead tracking | $750/mo or setup + $500/mo
Local Growth System | Improve website, Google presence, reviews, content, and follow-up | Landing page, local SEO, reviews, lead capture, follow-up, monthly report | $1,500/mo or setup + $1,000/mo
Pilot Offer | First 3 clients get reduced rate in exchange for documented case study if results are there | 90-day sprint with clear outcome tracking | Use to overcome no-case-study objection
Source / Basis | File | Used For
Agency positioning, rulebook, packages, KPIs | Marketing Agency Brain OS.docx | Core offer, weekly scorecard, 80/20 operating logic
Roles and ownership | Delko_Partnership_Agreement_50-50.docx | Keveen/Jack lanes and 90-day review metrics
Original roadmap | 90 day plan.pdf | Condensed into action-first workflow
Sales system | Agency_Sales_System.docx | Home services focus, outreach, discovery, proposal sequence
AI search positioning | Brand Visibility in the AI search era.pdf | Future positioning layer, not first 14-day priority
Professional services playbook | BGC_Sales_Playbook.docx | Later expansion into law/financial advisors